## Sheet1
Todos | Notes | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | Juni |  |  |  | July
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Create Mockup | bar: February 1 to February 2
Create API Spesification | bar: February 3
Create ERD | bar: February 4
Create HTML Template | bar: March 1
BACK END (Web Service)
Room Manage | bar: March 2 to March 3
Office Manage | bar: March 4
Employee Manage | bar: April 1
Booking Manage | bar: April 2 to April 3
FRONT END
Admin
CRUD Office | bar: April 4 to May 1
CRUD Room | bar: May 2
View All Booking | bar: May 3 to May 4
Customer
View All Booking | bar: Juni 1 to Juni 2
Create Booking | bar: Juni 3 to Juni 4
View My Booking | bar: July 1
Auth
Login & Register | bar: July 2 to July 4